## Management
Group Members | Role | Febuary (10-28) | March (1-14) | March (15-31) | April (1-15) | April (16-30) | May (1-15) | May (16-31) | June
Berk Yalçınkaya | Project Manager | * Define project scope * Document requirements * Create 8-week sprint roadmap | * Track tasks and progress * Prepare weekly report | * Project Manager * Coordinate testing process | * Review sprint progress | * Ensure requirements alignment | * Collect usability feedback | * Organize full system testing | * Prepare final documentation * Organize presentation
Hıdır Işıkbaş | Frontend Developer | * UI/UX plan (Catalog, Detail, Auth, Admin) * Set up React routing & component structure * Define frontend API services & auth flow | * Build Login/Register UI + validation * Protected routes (catalog requires login) * Base layout (navbar/footer, responsive) | * Catalog UI (cards, filters, sorting) * Connect Catalog to API * Car Detail UI (gallery, specs) | * Favorites UI (add/remove, list) * Contact Form UI + submit flow * Loading/error states & state management | * Admin UI (car add/edit forms) * Image upload + delete UI * Brand management CRUD screens | * Responsive + accessibility improvements * Styling consistency (components) * Price history/notify settings UI (if scope) | * End-to-end integration fixes * Edge cases + empty states * Usability feedback fixes | * Frontend production build * Frontend docs (setup/build/env) * Support final demo/presentation
Asya Yayla | Risk Manager | * Identify technical risks (API failure, data loss, etc.) * Prepare risk matrix | * Test API connectivity * Review data persistence risks | * Test API failure scenarios | * Analyze invalid data entry risks | * Evaluate data conflict risks | * Analyze accidental deletion risk | * Conduct final risk assessment * Check for critical vulnerabilities | * Perform live environment risk analysis * Approve release
Burak Bayraktar | Database Developer | * Design User data model * Define LocalStorage data structure | * Implement LocalStorage data source * Develop read/write functions | * Test BrandEntity and car table synchronization | * Test CRUD operations | * Test data consistency after updates | * Verify DataBase and tables consistency after deletion | * Perform data integrity testing | * Test data persistence in production
Hasan Eren Ertekin | Backend Developer | *Design entity models (Car, Brand, BaseEntity) *Define Car–Brand relationship (1-N) | *Implement DTO structure (AddCarDto, AddBrandDto) *Setup EF Core migrations *Configure Swagger for API testing | *Implement Brand entity and table *Resolve foreign key & migration conflicts | *Implement Brand CRUD endpoints | *Test API via Swagger | *Refactor controllers and DTO usage | *Final API testing | *Prepare backend documentation

## Budget
Period | Active Members | Duration (days) | Total Cost ($)
Febuary (10-28) | 5 | 19 | 11305
March (1-14) | 5 | 14 | 8330
March (15-31) | 5 | 17 | 10115
April (1-15) | 5 | 15 | 8925
April (16-30) | 5 | 15 | 8925
May (1-15) | 5 | 15 | 8925
May (16-31) | 5 | 16 | 9520
June | 5 | 15 | 8925

## CarGallery_Week2
CarGallery Strategic and Technical Overview
Presentation-ready summary for project management review and final deck support
No | Section | Focus Area | Key Message | CarGallery-Specific Notes
1 | Executive Summary | Business / Product | What it is and why it matters. | CarGallery is a dealership catalog + admin system. Admins manage cars/brands/images/users; registered customers browse, favorite, and send contact requests.
2 | Product Description and Vision | Business / Product | Users, problem, and growth vision. | For dealership staff and registered customers. Replaces spreadsheet tracking with searchable listings and a scalable engagement platform.
3 | Core Features and Capabilities | Business / Product | MVP + planned capabilities. | MVP: auth, catalog, filters, car details, admin car/brand/user CRUD, image upload. Planned: block guests, favorites, price history + alerts, contact request workflow.
4 | Technical Architecture and Infrastructure | Architecture / Security | System structure and hosting. | React (Vite) client calls ASP.NET Core Web API over HTTPS. Relational DB (SQLite dev; Postgres/MySQL ready); images stored on server/object storage.
5 | Technology Stack | Architecture / Security | Frameworks, database, tooling. | Frontend React + TypeScript; Backend ASP.NET Core + EF Core; DB SQLite. Tooling: Git, Swagger/Postman; CI-ready scripts.
6 | Security Architecture | Architecture / Security | How data and actions are protected. | HTTPS, hashed passwords, server-side JWT validation, RBAC on endpoints. Input validation, secure uploads, and admin action logs.
7 | Role and Authorization Management Model | Architecture / Security | Roles and permissions model. | Roles: Customer, Admin, Super Admin. Enforce access in the API (and UI) with least-privilege policies per endpoint.
8 | Clearance Level System | Architecture / Security | Access levels mapped to features. | Clearance: L0 guest (no catalog), L1 registered (view), L2 engaged (favorites/contact), L3 admin (manage), L4 super admin (role/security).
9 | User Experience and Interface | UX / Operations | Main screens and user flow. | Pages: login/register, catalog (search/filter/sort), car detail (gallery/specs), favorites/price tracking/contact (planned), admin panel (cars/brands/users). Responsive UI with clear feedback.
10 | Installation and Deployment | UX / Operations | How to run and deploy. | Local: run API + Vite, migrate/seed DB, set env vars. Deploy: build frontend, host API, configure prod DB/secrets/HTTPS, enable backups.
11 | Integration and Scalability | UX / Operations | Integrations and scaling approach. | Integrate email/SMS for alerts, analytics, and storage. Scale with pagination, caching, background jobs, and a production DB.
12 | Competitive Analysis and Differentiation | Strategy / Requirements | Differentiators vs alternatives. | More structured than social listings and safer than spreadsheets: access control, consistent data, and engagement tools (favorites/alerts/contact).
13 | Licensing and Commercial Model | Strategy / Requirements | Commercialization approach. | Academic prototype; can evolve into white-label SaaS with tiered subscriptions and add-ons (integrations, analytics, multi-branch).
14 | Technical Requirements | Strategy / Requirements | Non-functional requirements. | NFRs: fast catalog with pagination, secure auth/RBAC/uploads, logging + backups, maintainable code, basic tests and monitoring.
Color Guide: Business / Product = orange, Architecture / Security = blue, UX / Operations = green, Strategy / Requirements = yellow
Note on E6: Prepared as a presentation-friendly overview sheet for the CarGallery project.