## Management
Group Members | Role | Febuary (10-28) | March (1-14) | March (15-31) | April (1-15) | April (16-30) | May (1-15) | May (16-31) | June
Berk Yalçınkaya | Project Manager | * Define project scope * Document requirements * Create 8-week sprint roadmap | * Track tasks and progress * Prepare weekly report | * Project Manager * Coordinate testing process | * Review sprint progress | * Ensure requirements alignment | * Collect usability feedback | * Organize full system testing | * Prepare final documentation * Organize presentation
Hıdır Işıkbaş | Frontend Developer | * UI/UX plan (Catalog, Detail, Auth, Admin) * Set up React routing & component structure * Define frontend API services & auth flow | * Build Login/Register UI + validation * Protected routes (catalog requires login) * Base layout (navbar/footer, responsive) | * Catalog UI (cards, filters, sorting) * Connect Catalog to API * Car Detail UI (gallery, specs) | * Favorites UI (add/remove, list) * Contact Form UI + submit flow * Loading/error states & state management | * Admin UI (car add/edit forms) * Image upload + delete UI * Brand management CRUD screens | * Responsive + accessibility improvements * Styling consistency (components) * Price history/notify settings UI (if scope) | * End-to-end integration fixes * Edge cases + empty states * Usability feedback fixes | * Frontend production build * Frontend docs (setup/build/env) * Support final demo/presentation
Asya Yayla | Risk Manager | * Identify technical risks (API failure, data loss, etc.) * Prepare risk matrix | * Test API connectivity * Review data persistence risks | * Test API failure scenarios | * Analyze invalid data entry risks | * Evaluate data conflict risks | * Analyze accidental deletion risk | * Conduct final risk assessment * Check for critical vulnerabilities | * Perform live environment risk analysis * Approve release
Burak Bayraktar | Database Developer | * Design User data model * Define LocalStorage data structure | * Implement LocalStorage data source * Develop read/write functions | * Test BrandEntity and car table synchronization | * Test CRUD operations | * Test data consistency after updates | * Verify DataBase and tables consistency after deletion | * Perform data integrity testing | * Test data persistence in production
Hasan Eren Ertekin | Backend Developer | *Design entity models (Car, Brand, BaseEntity) *Define Car–Brand relationship (1-N) | *Implement DTO structure (AddCarDto, AddBrandDto) *Setup EF Core migrations *Configure Swagger for API testing | *Implement Brand entity and table *Resolve foreign key & migration conflicts | *Implement Brand CRUD endpoints | *Test API via Swagger | *Refactor controllers and DTO usage | *Final API testing | *Prepare backend documentation

## Budget
Period | Active Members | Duration (days) | Total Cost ($)
Febuary (10-28) | 5 | 19 | 11305
March (1-14) | 5 | 14 | 8330
March (15-31) | 5 | 17 | 10115
April (1-15) | 5 | 15 | 8925
April (16-30) | 5 | 15 | 8925
May (1-15) | 5 | 15 | 8925
May (16-31) | 5 | 16 | 9520
June | 5 | 15 | 8925

## CarGallery_Week2
CarGallery Strategic and Technical Overview
Presentation-ready summary for project management review and final deck support
No | Section | Focus Area | Key Message | CarGallery-Specific Notes
1 | Executive Summary | Business / Product | What it is and why it matters. | CarGallery is a dealership catalog + admin system. Admins manage cars/brands/images/users; registered customers browse, favorite, and send contact requests.
2 | Product Description and Vision | Business / Product | Users, problem, and growth vision. | For dealership staff and registered customers. Replaces spreadsheet tracking with searchable listings and a scalable engagement platform.
3 | Core Features and Capabilities | Business / Product | MVP + planned capabilities. | MVP: auth, catalog, filters, car details, admin car/brand/user CRUD, image upload. Planned: block guests, favorites, price history + alerts, contact request workflow.
4 | Technical Architecture and Infrastructure | Architecture / Security | System structure and hosting. | React (Vite) client calls ASP.NET Core Web API over HTTPS. Relational DB (SQLite dev; Postgres/MySQL ready); images stored on server/object storage.
5 | Technology Stack | Architecture / Security | Frameworks, database, tooling. | Frontend React + TypeScript; Backend ASP.NET Core + EF Core; DB SQLite. Tooling: Git, Swagger/Postman; CI-ready scripts.
6 | Security Architecture | Architecture / Security | How data and actions are protected. | HTTPS, hashed passwords, server-side JWT validation, RBAC on endpoints. Input validation, secure uploads, and admin action logs.
7 | Role and Authorization Management Model | Architecture / Security | Roles and permissions model. | Roles: Customer, Admin, Super Admin. Enforce access in the API (and UI) with least-privilege policies per endpoint.
8 | Clearance Level System | Architecture / Security | Access levels mapped to features. | Clearance: L0 guest (no catalog), L1 registered (view), L2 engaged (favorites/contact), L3 admin (manage), L4 super admin (role/security).
9 | User Experience and Interface | UX / Operations | Main screens and user flow. | Pages: login/register, catalog (search/filter/sort), car detail (gallery/specs), favorites/price tracking/contact (planned), admin panel (cars/brands/users). Responsive UI with clear feedback.
10 | Installation and Deployment | UX / Operations | How to run and deploy. | Local: run API + Vite, migrate/seed DB, set env vars. Deploy: build frontend, host API, configure prod DB/secrets/HTTPS, enable backups.
11 | Integration and Scalability | UX / Operations | Integrations and scaling approach. | Integrate email/SMS for alerts, analytics, and storage. Scale with pagination, caching, background jobs, and a production DB.
12 | Competitive Analysis and Differentiation | Strategy / Requirements | Differentiators vs alternatives. | More structured than social listings and safer than spreadsheets: access control, consistent data, and engagement tools (favorites/alerts/contact).
13 | Licensing and Commercial Model | Strategy / Requirements | Commercialization approach. | Academic prototype; can evolve into white-label SaaS with tiered subscriptions and add-ons (integrations, analytics, multi-branch).
14 | Technical Requirements | Strategy / Requirements | Non-functional requirements. | NFRs: fast catalog with pagination, secure auth/RBAC/uploads, logging + backups, maintainable code, basic tests and monitoring.
Color Guide: Business / Product = orange, Architecture / Security = blue, UX / Operations = green, Strategy / Requirements = yellow
Note on E6: Prepared as a presentation-friendly overview sheet for the CarGallery project.

## CarGallery_Week3
CarGallery Risk Management, Testing & Success Criteria
Week 3 package: risk register + matrix, security/privacy controls, roadmap, validation/testing plan, and measurable success criteria
1) Risk Analysis — Risk Register (Identification, Assessment, Mitigation)
Risk ID | Risk Description | Category | Probability (1–5) | Impact (1–5) | Score | Level | Owner | Mitigation / Preventive Actions
R1 | Server-side RBAC not enforced (admin endpoints callable by non-admin). | Security | 4 | 5 | 20 | Critical | Asya Yayla | Implement JWT validation + [Authorize] on API; role checks (Admin/SuperAdmin); deny-by-default; add 401/403 tests.
R2 | Catalog visibility rule may be violated (guests can browse cars). | Requirements | 3 | 4 | 12 | High | Hıdır Işıkbaş | Add protected routes on frontend + backend auth guard; redirect guests to login; add acceptance test.
R3 | File upload vulnerabilities (malicious files, path traversal, large payload). | Security | 3 | 5 | 15 | High | Hasan Eren Ertekin | Whitelist MIME/ext, size limits, random filenames, store outside webroot; restrict delete to admin; audit logs.
R4 | Scope creep: favorites + price tracking + notifications may exceed June timeline. | Scope/Schedule | 4 | 4 | 16 | Critical | Berk Yalçınkaya | Freeze MVP scope; prioritize (MVP vs Phase‑2); weekly review; timebox features; define must-have list.
R5 | Database evolution issues (migrations, JSON ImageUrls, schema conflicts). | Technical | 3 | 4 | 12 | High | Burak Bayraktar | Use EF migrations; version schema; seed data; validate ImageUrls conversion; rollback plan.
R6 | Performance issues with growing inventory (no pagination/caching). | Technical | 3 | 3 | 9 | Medium | Hasan Eren Ertekin | Add pagination + indexes; optimize queries; image thumbnails; basic load test and targets.
R7 | Data loss/corruption risk (single local SQLite DB, weak backup). | Operations | 2 | 4 | 8 | Medium | Burak Bayraktar | Automated backups; export/import scripts; integrity checks; plan prod DB for deployment.
R8 | Team coordination risk (role changes, merge conflicts, unclear ownership). | Team | 3 | 3 | 9 | Medium | Berk Yalçınkaya | Define ownership; branch strategy; PR reviews; weekly standups; update task board.
R9 | Deployment risks (HTTPS cert, env vars, image storage path/permissions). | Operations | 2 | 4 | 8 | Medium | Berk Yalçınkaya | Deployment checklist; env templates; staging test; document storage + permissions.
R10 | Privacy compliance gaps (PII retention, deletion policy, logs). | Data Privacy | 2 | 4 | 8 | Medium | Asya Yayla | Minimize PII; define retention; soft delete policy; access logging; privacy note.
R11 | Authentication hardening missing (token expiry, rate-limit, brute-force). | Security | 3 | 4 | 12 | High | Asya Yayla | Short-lived JWT; rate-limit login; lockout; monitoring; log suspicious attempts.
R12 | UI/UX regressions (responsive/a11y, confusing admin flows). | UX | 3 | 3 | 9 | Medium | Hıdır Işıkbaş | Responsive checklist; basic a11y; consistent validation; usability test and fix top issues.
1-3 Risk Matrix (Probability × Impact)
| Impact (1 = Low, 5 = Very High) | [5 empty] | Legend
|  | 1 | 2 | 3 | 4 | 5 | Low (1–4)
Probability (1=Low 5=Very High) | 5 | 5 | 10 | 15 | 20 | 25 | Medium (5–9)
| 4 | 4 | 8 | 12 | 16 | 20 | High (10–15)
| 3 | 3 | 6 | 9 | 12 | 15 | Critical (16–25)
| 2 | 2 | 4 | 6 | 8 | 10
| 1 | 1 | 2 | 3 | 4 | 5
2) Code Security & Data Privacy — Controls Checklist
ID | Control | Purpose | Status | Owner | Evidence / Notes (what to show in demo/report)
S1 | HTTPS everywhere | Protect credentials & data in transit | Planned | Berk Yalçınkaya | Production deployment: enforce HTTPS and HSTS.
S2 | Password hashing | Protect passwords at rest | Done | Backend | ASP.NET Identity hashing; no plaintext storage.
S3 | Server-side JWT validation | Stop token spoofing / fake tokens | In progress | Hasan Eren Ertekin | Enable auth middleware; verify signature + expiry.
S4 | RBAC on API endpoints | Prevent non-admin CRUD access | Planned | Hasan Eren Ertekin | Authorize roles on Cars/Brands/Users; negative tests (401/403).
S5 | Frontend protected routes | Block guests from catalog/admin UI | Planned | Hıdır Işıkbaş | Route guards; redirect to login; show 403 page.
S6 | Secure file upload rules | Prevent malware & traversal | Planned | Hasan Eren Ertekin | MIME/ext whitelist, size limits, random names, storage outside webroot.
S7 | Input validation & safe errors | Reduce injection and crashes | In progress | Backend | DTO validation; consistent error responses; logging.
S8 | Rate limiting / lockout | Reduce brute-force attacks | Planned | Asya Yayla | Rate limit login; lockout; log suspicious attempts.
S9 | Admin audit logging | Trace changes & accountability | Planned | Asya Yayla | Log create/update/delete with userId + timestamp.
P1 | PII minimization | Store only needed user data | Planned | Asya Yayla | Document stored fields; avoid extra personal data.
P2 | Account deletion policy | Privacy + recovery | In progress | Backend | Soft delete; define retention; document in report.
P3 | Backup & restore plan | Reduce data loss risk | Planned | Burak Bayraktar | SQLite backup/restore steps; schedule weekly backup.
3) Implementation Roadmap (March–June)
Phase / Timebox | Goal | Key Deliverables |  |  |  |  | Owner(s) | Notes / Dependencies
Week 3 (next week) | Weekly submission package | Complete missing doc sections; risk register + matrix; security/privacy checklist; testing plan; success criteria; update Jira/board |  |  |  |  | Berk + Asya | Required for next week
March | Security baseline & access control | JWT validation; RBAC on endpoints; protect catalog for guests; upload constraints; error handling |  |  |  |  | Hasan + Hıdır | Reduces R1/R2/R3
April | Engagement workflow | Favorites + contact request flow; admin review page; UI polish; DB updates |  |  |  |  | Hıdır + Hasan + Burak | Timebox to avoid scope creep
May | Alerts + quality gate | Price history; notification stub; pagination/perf; usability tests; bug fixes |  |  |  |  | Hasan + Berk | If alerts out-of-scope: document as future work
June | Release & final presentation | Deployment guide; final E2E testing; backup plan; final slides + rehearsal |  |  |  |  | Berk + Team | Staging run-through before demo
4) Validation and Testing Plan
Test Layer | Scope (what is tested) | Method / Tools | Validation Metrics | Owner | When | Evidence / Output
Unit (Backend) | DTO validation, service logic, helpers | xUnit/NUnit (optional) + assertions | Pass rate; critical-path coverage | Hasan | Mar–May | Test report / screenshots
Integration (API) | Auth; Cars/Brands CRUD; Upload/delete image | Postman + Swagger; negative tests | Correct 200/401/403; stable errors | Hasan | Mar–Jun | Postman collection + run output
UI (Frontend) | Login, protected routes, catalog filters, admin forms | Manual checklist + optional RTL | No console errors; checklist pass | Hıdır | Mar–Jun | Checklist + screenshots
E2E (Smoke) | Register → browse → detail → contact/favorite | Playwright/Cypress (optional) | Critical flow pass rate ≥ 95% | Berk + Hıdır | May–Jun | Recorded demo run
Security validation | Auth bypass; role escalation; upload abuse | OWASP checklist + targeted tests | 0 critical vulns; no unauthorized admin ops | Asya | Mar–Jun | Security checklist
Performance | Catalog latency with pagination | k6/JMeter (light) | API latency target (e.g., <1s); err <1% | Hasan + Burak | May | Perf notes
Data integrity | CRUD consistency; backup/restore rehearsal | DB checks; restore test | No orphans; restore success | Burak | May–Jun | Restore log
5) Success Criteria (How we determine project success)
Category | Success Criterion | Target | How Measured / Evidence
Security | Admin endpoints protected by server-side RBAC | Non-admin receives 403; admin succeeds | API tests showing 401/403 + successful admin actions
Access Control | Guests cannot view catalog | Guest redirected to login; API returns 401/403 | Demo: open catalog as guest → blocked
Functionality | Admin can add/edit/delete cars + manage brands | All CRUD flows work without errors | Demo checklist + screenshots
Media Handling | Image upload/delete works safely | Only allowed types; size limit enforced | Upload tests + stored file path evidence
Quality | Test plan executed | ≥ 90% planned test cases passed; no P0 bugs | Test checklist with pass/fail summary
Performance | Catalog endpoint responsive | Paged listing returns within target (e.g., <1s on test env) | Timing logs / perf notes
Documentation | Deployment + usage documented | README + deployment checklist complete | Docs in repo + instructor review
Project Management | Plan delivered to June with weekly tracking | Updated management sheet + weekly reports | Excel management table + Jira board snapshots
Week 3 Update: New Requirements (City + Multi-Gallery)
Feature | What changes | Priority | Owner | Target week | Notes
City selection (entry) | User selects city first; system shows galleries in that city before catalog. | High | Frontend | W4 | Store selection (session/localStorage).
Gallery directory | List galleries by city; search/sort; show contact + inventory count. | High | Frontend | W5 | Pagination for many galleries.
Multi-gallery data model | Add Gallery + City entities; cars/brands/users scoped to GalleryId. | High | Backend | W4–W5 | DB migration + seed default gallery.
Gallery-scoped catalog | All car endpoints filtered by GalleryId; UI routes include selected gallery. | High | Backend+Frontend | W5 | Prevent cross-gallery access.
SuperAdmin functions | Create galleries + assign admins to a gallery. | Medium | Backend | W6 | RBAC policies and audit logs.
Week 3 Update: Additional Risks for Multi-Gallery Scope
Risk ID | Risk | Probability | Impact | Risk Level | Mitigation / Preventive Action | Owner
R-MG-01 | Cross-gallery data leakage if GalleryId filtering is missed in any endpoint. | Medium | High | High | Enforce GalleryId scoping everywhere; add automated tests; code review checklist. | Backend Lead
R-MG-02 | DB redesign/migration delays affect schedule. | Medium | High | High | Finalize schema early; incremental migrations; buffer time; keep rollback plan. | PM
R-MG-03 | Wrong RBAC (SuperAdmin/Admin per gallery) causes security gaps. | Low | High | Medium | Policy-based authorization; negative tests; audit logs. | Backend Lead
R-MG-04 | User confusion in city→gallery→catalog flow reduces engagement. | Medium | Medium | Medium | Breadcrumbs + clear CTAs; keep selection visible; quick usability test. | Frontend Lead
R-MG-05 | Performance issues with many galleries/cars. | Medium | Medium | Medium | Pagination; DB indexes (CityId/GalleryId); basic load testing. | Backend+Frontend
Week 3 Update: Validation & Testing Plan (City + Multi-Gallery)
Test type | What we validate | Tools/Method | Owner | When | Pass criteria
Unit tests (API) | GalleryId scoping, role checks, input validation. | xUnit + EF InMemory/Test DB | Backend | W5–W6 | All critical tests pass, coverage on core endpoints.
Integration tests | City→gallery endpoints + gallery-scoped catalog; negative leakage tests. | Postman/Newman or TestServer | Backend | W6 | No cross-gallery access; correct status codes.
Frontend E2E smoke | City select → gallery select → catalog → detail. | Playwright/Cypress | Frontend | W6 | Happy path completes without errors.
UX validation | Users can reach a car detail within 30s after city selection. | 5-user quick test + notes | PM+FE | W6 | ≥80% complete task; issues logged.
Performance check | Gallery list + catalog response time with pagination. | k6/JMeter quick run | Backend | W7 | p95 < 1.5s on test env (target).